# Software Project Planning and Scheduling

Experiment 12  |  WebShield Advanced Phishing Detection System

| Student name | Roll number | Class / division | Subject |
| --- | --- | --- | --- |
| Aditya Madhukar Mane | A102 | TY-CSE (A) | Software Engineering |

# Aim

To apply software project planning and scheduling techniques—WBS, Basic COCOMO, CPM, PERT, Gantt scheduling, resource and cost planning, risk planning, milestones, and Earned Value Management—to the WebShield phishing detection project.

# Project summary

WebShield is a web application intended to analyze submitted URLs and report a safety classification. The repository describes three labels—Safe, Suspicious, and Phishing—and lists Python/Flask, HTML, CSS, JavaScript, scikit-learn, pandas, and NumPy. This plan models the work needed to specify, prepare the data and model, build the web workflow, integrate, test, and package the application.

Evidence boundary: the public repository summary was available, but its source files and measured line count could not be inspected for this report. KLOC, durations, team roles, rates, and the EVM status are therefore planning assumptions for the classroom exercise, not verified project history. Replace them with repository counts, actual team details, and actual records when available. Project source: github.com/AdityaMane231105/WebShield-Cybersecurity-Scanner.

# Learning objectives

Decompose WebShield into deliverables and schedulable work packages.

Estimate effort and schedule with Basic COCOMO and compare against bottom-up effort.

Sequence activities and identify the critical path and schedule slack.

Use PERT to quantify schedule uncertainty and prepare a Gantt chart.

Plan responsibilities, cost, risks, milestones, and progress measurement.

# 1. Scope and assumptions

In scope: requirements and URL feature definition; dataset preparation; model training and evaluation; application/interface design; Flask request and result flow; model integration; functional and basic security testing; packaging and user documentation. Out of scope for this plan: continuously crawling submitted websites, a production threat-intelligence service, and guarantees that any classifier will detect every phishing page.

| Planning assumption | Value used | Reason / action to verify |
| --- | --- | --- |
| Project mode | Organic, small and familiar | Same Basic COCOMO mode used in the experiment guide; reassess if constraints are high. |
| Estimated code size | 1.8 KLOC | Illustrative estimate only; count project source files and exclude generated/vendor files. |
| Schedule calendar | 5 working days per week | Classroom planning convention; exclude holidays/exam days. |
| Team | 4 student roles (S1–S4) | Roles are placeholders; replace with actual names and availability. |
| Cost rate | ₹1,000 per person-day | Illustrative labor valuation from guide; replace if instructor specifies another rate. |
| Duration basis | Working days | Task duration is elapsed work time; effort is person-days and can differ when parallel work is used. |

# 2. Work Breakdown Structure

| WBS | Work package | Deliverable / completion evidence |
| --- | --- | --- |
| 1.0 | Project management | Approved plan, task ownership, status updates |
| 2.0 | Requirements and URL feature definition | SRS, input/output rules, acceptance criteria |
| 3.0 | Data and model preparation | Clean dataset, feature list, trained model, evaluation record |
| 3.1 | Dataset review and preparation | Documented labels, cleaning and split |
| 3.2 | Feature engineering and model training | Reproducible feature/model pipeline |
| 4.0 | Application design and implementation | Runnable WebShield application |
| 4.1 | Architecture and interface design | Component flow and screen design |
| 4.2 | Flask URL submission and result flow | Validated input and response page |
| 4.3 | Model inference integration | Application calls saved model and renders class |
| 5.0 | Integration and testing | Integrated build, test cases and defect log |
| 6.0 | Packaging and documentation | Setup instructions, user guide, demonstration build |

# 3. Size, effort and schedule estimation using COCOMO

Basic COCOMO Organic equations from the experiment guide: Effort E = 2.4 × (KLOC)^1.05 person-months; development time D = 2.5 × E^0.38 months. For this classroom plan, KLOC is assumed to be 1.8 pending a count of WebShield’s own source code.

| Calculation | Result |
| --- | --- |
| Effort: 2.4 × 1.8^1.05 | 4.45 person-months (approx.) |
| Person-day equivalent at 20 days/month | 4.45 × 20 = 89.0 person-days |
| Nominal development time: 2.5 × 4.45^0.38 | 4.41 months (approx.) |
| Average staffing implied by E ÷ D | 4.45 ÷ 4.41 = 1.01 persons (approx.) |
| Bottom-up activity estimate (Section 4) | 94 person-days |
| Comparison | Bottom-up estimate is about 5.0 person-days (about 6%) above COCOMO; plausible for an early estimate. |

Interpretation: the 37-working-day network schedule is an accelerated classroom target supported by parallel work from four people. It is shorter than the nominal COCOMO time of about 4.41 months, so coordination, model/data uncertainty, and team availability are schedule risks. COCOMO is a coarse size-based estimate; recalibrate KLOC and assumptions before treating it as a forecast.

# 4. Activities, dependencies and effort

| ID | Activity | Duration (days) | Predecessor(s) | Effort (person-days) |
| --- | --- | --- | --- | --- |
| A | Requirements and acceptance criteria | 5 | — | 8 |
| B | System and model workflow design | 6 | A | 10 |
| C | Dataset preparation and feature definition | 6 | B | 12 |
| D | Architecture and UI design | 5 | B | 10 |
| E | Model training and evaluation | 6 | C | 12 |
| F | Flask interface and URL workflow | 8 | D | 16 |
| G | Integrate model and application | 4 | E, F | 8 |
| H | Functional, validation and security testing | 6 | G | 12 |
| I | Package, deploy and document | 3 | H | 6 |

Total bottom-up effort = 94 person-days. The two parallel streams after design are data/model work (C→E) and application work (D→F); both must finish before integration (G).

# 5. CPM network and critical path

Network: Start → A → B → {C → E, D → F} → G → H → I → Finish. The braces indicate parallel branches; G waits for both E and F.

| ID | Dur. | ES | EF | LS | LF | Slack | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 5 | 0 | 5 | 0 | 5 | 0 | Yes |
| B | 6 | 5 | 11 | 5 | 11 | 0 | Yes |
| C | 6 | 11 | 17 | 12 | 18 | 1 | No |
| D | 5 | 11 | 16 | 11 | 16 | 0 | Yes |
| E | 6 | 17 | 23 | 18 | 24 | 1 | No |
| F | 8 | 16 | 24 | 16 | 24 | 0 | Yes |
| G | 4 | 24 | 28 | 24 | 28 | 0 | Yes |
| H | 6 | 28 | 34 | 28 | 34 | 0 | Yes |
| I | 3 | 34 | 37 | 34 | 37 | 0 | Yes |

Critical path: A → B → D → F → G → H → I. Minimum planned duration: 37 working days (about 7.4 five-day weeks). C and E each have one working day of total slack; delaying either beyond that slack delays integration and the project finish.

# 6. PERT analysis

Three-point estimates are planning judgments in working days. TE = (O + 4M + P) / 6; variance = ((P − O) / 6)^2.

| ID / critical activity | O | M | P | TE | Variance |
| --- | --- | --- | --- | --- | --- |
| A Requirements | 3 | 5 | 7 | 5.00 | 0.44 |
| B System/model design | 4 | 6 | 8 | 6.00 | 0.44 |
| D Architecture/UI design | 3 | 5 | 7 | 5.00 | 0.44 |
| F Flask workflow | 6 | 8 | 10 | 8.00 | 0.44 |
| G Integration | 3 | 4 | 5 | 4.00 | 0.11 |
| H Testing | 4 | 6 | 8 | 6.00 | 0.44 |
| I Package/document | 2 | 3 | 4 | 3.00 | 0.11 |
| Critical path total |  |  |  | 37.00 | 2.44 |

Critical-path standard deviation σ = √2.44 = 1.56 days (approx.). For a 40-working-day target, Z = (40 − 37) / 1.56 = 1.92, giving an approximate completion probability of 97% under the normal approximation. The estimate assumes independent activity durations and should be treated as a planning aid, not a guarantee.

# 7. Gantt schedule

The following schedule uses day 1 as the first working day. Week 1 = days 1–5, Week 2 = days 6–10, and so on. A bar in a week means the activity overlaps at least one working day in that week.

| Activity | Days | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A Requirements | 1–5 | ■ |  |  |  |  |  |  |  |
| B Design | 6–11 |  | ■ | ■ |  |  |  |  |  |
| C Dataset/features | 12–17 |  |  | ■ | ■ |  |  |  |  |
| D UI/architecture | 12–16 |  |  | ■ | ■ |  |  |  |  |
| E Model training | 18–23 |  |  |  | ■ | ■ |  |  |  |
| F Flask workflow | 17–24 |  |  |  | ■ | ■ |  |  |  |
| G Integration | 25–28 |  |  |  |  | ■ | ■ |  |  |
| H Testing | 29–34 |  |  |  |  |  | ■ | ■ |  |
| I Package/docs | 35–37 |  |  |  |  |  |  | ■ | ■ |

Milestone targets use the same day count: SRS approved (Day 5), design approved (Day 11 for system/model and Day 16 for UI/architecture), model and Flask streams ready (Day 23/24), integrated build (Day 28), testing complete (Day 34), package and delivery (Day 37).

# 8. Resource allocation and cost plan

| ID | Activity | Assigned role(s) | Effort (pd) | Cost at ₹1,000/pd |
| --- | --- | --- | --- | --- |
| A | Requirements | S1 Analyst/PM; S2 Data | 8 | ₹8,000 |
| B | System/model workflow design | S1; S2 | 10 | ₹10,000 |
| C | Dataset/features | S2; S3 ML | 12 | ₹12,000 |
| D | Architecture/UI | S1; S4 App | 10 | ₹10,000 |
| E | Model training | S3 ML | 12 | ₹12,000 |
| F | Flask workflow | S4 App; S1 | 16 | ₹16,000 |
| G | Integration | S3; S4 | 8 | ₹8,000 |
| H | Testing | S2; S4 | 12 | ₹12,000 |
| I | Packaging/docs | S1; S2 | 6 | ₹6,000 |
| Total labor BAC |  |  | 94 | ₹94,000 |

| Budget item | Amount |
| --- | --- |
| Base labor budget (BAC) | ₹94,000 |
| Contingency reserve (10% of BAC) | ₹9,400 |
| Planned total budget including reserve | ₹103,400 |

S1–S4 are role placeholders for four students, not confirmed assignments. The assumed rate values student effort for the exercise; it is not a claim about actual cash expenditure. Cost excludes hosting or other expenses unless the instructor asks to include them.

# 9. Risk plan

| Risk | Probability / impact | Response / mitigation | Owner |
| --- | --- | --- | --- |
| Training data is unbalanced, mislabeled, or not representative | Medium / High | Inspect label counts and sources; use a held-out evaluation set; document dataset limitations. | S2, S3 |
| False safe or phishing classifications | Medium / High | Track precision/recall by class; test borderline URLs; display result as an indicator, not a guarantee. | S3, S4 |
| Integration mismatch between saved model and Flask app | Medium / Medium | Agree input feature schema early; create a small end-to-end integration test before feature freeze. | S3, S4 |
| Compressed schedule or exams reduce availability | High / High | Protect critical-path tasks; maintain one-day slack on model branch; review progress weekly and agree scope priorities. | S1 |
| URL parsing or unsafe input handling | Medium / High | Validate and normalize input; reject malformed values; test long, encoded, and unusual URLs. | S4 |
| Testing time is squeezed by late integration | Medium / High | Prepare test cases during requirements; run module checks while coding; reserve six days for system testing. | S2, S4 |
| KLOC and effort estimate are inaccurate | Medium / Medium | Measure project-owned source lines; revisit estimates after scope and code inventory. | S1 |

# 10. Milestone plan

| Milestone | Acceptance evidence | Target day |
| --- | --- | --- |
| M1 Requirements approved | Scope, URL inputs/outputs, acceptance criteria agreed | 5 |
| M2 Design approved | System/model flow and UI/architecture agreed | 16 |
| M3 Work streams ready | Model evaluation recorded and Flask workflow implemented | 24 |
| M4 Integrated build | Web app calls model and displays classification | 28 |
| M5 Testing complete | Test cases executed; defects recorded and dispositioned | 34 |
| M6 Delivery | Runnable package and user/setup documentation | 37 |

# 11. Earned Value Management checkpoint

Worked classroom scenario at the end of Day 20. This is simulated because no actual cost ledger or progress record was provided. Planned completion by Day 20 includes A, B, C, and D complete; 3 of 6 planned days of E; and 3 of 8 planned days of F.

| Measure | Calculation | Value |
| --- | --- | --- |
| BAC | 94 person-days × ₹1,000 | ₹94,000 |
| PV | A+B+C+D (₹40,000) + 3/6 of E (₹6,000) + 3/8 of F (₹6,000) | ₹52,000 |
| EV | Assumed actual: A+B+C+D complete and half of E complete | ₹46,000 |
| AC | Assumed cumulative actual cost at Day 20 | ₹55,000 |
| SPI | EV / PV = 46,000 / 52,000 | 0.88 |
| CPI | EV / AC = 46,000 / 55,000 | 0.84 |
| EAC | BAC / CPI = 94,000 / 0.836 | approx. ₹112,400 |

Interpretation: SPI < 1 indicates the simulated project is behind its planned progress; CPI < 1 indicates more cost has been spent per unit of earned work than planned. EAC exceeds BAC by about ₹18,400 and the ₹103,400 budget including reserve by about ₹9,000. Corrective action: review the remaining model work and the critical application branch, resolve blockers, protect the test window, and reforecast effort and cost before changing scope.

# 12. Comparison of planning techniques

| Technique | Use in WebShield plan | Main output |
| --- | --- | --- |
| WBS | Break project deliverables into owned work packages | Scope and work package hierarchy |
| COCOMO | Estimate size-based effort and nominal development time | Person-months and months |
| CPM | Sequence activities with fixed durations | Critical path and slack |
| PERT | Represent duration uncertainty with O/M/P estimates | Expected duration, variance, target-date probability |
| Gantt | Communicate planned overlaps across weeks | Timeline bars and milestone placement |
| Resource/cost plan | Assign role placeholders and value effort | Workload and budget baseline |
| EVM | Compare planned value, completed value, and actual cost | SPI, CPI, EAC and corrective action |

# Observations

The WBS maps WebShield requirements, data/model work, web implementation, integration, testing, and delivery into planned work packages.

The assumed Basic COCOMO estimate is about 88.6 person-days; the bottom-up plan is 94 person-days. Both are early planning estimates and depend on validating the assumed 1.8 KLOC.

CPM gives a 37-working-day schedule. The application branch is critical; the data/model branch has one day of slack.

PERT estimates about 97% probability of completing within 40 working days under the stated assumptions and normal approximation.

In the simulated Day 20 checkpoint, SPI and CPI are both below 1, so the plan calls for corrective action and a revised forecast.

# Result

Software project planning and scheduling techniques were applied to WebShield. Under the stated classroom assumptions, the project plan estimates 94 person-days of bottom-up effort, a 37-working-day critical-path schedule, a base labor budget of ₹94,000, and a ₹103,400 budget including 10% contingency. CPM identifies A–B–D–F–G–H–I as the critical path, while PERT estimates approximately 97% probability of completion within 40 working days. A simulated EVM checkpoint demonstrates how schedule and cost variance can be identified and acted upon.